## Sprint Tracker
AES SERVICE APPLICATION — SPRINT 1 (DESIGN SPRINT)
Sprint No.: 1 — Design Sprint |  |  |  | Sprint Dates: 01 Jul 2026 → 14 Jul 2026
🎯 SPRINT 1 GOAL: Deliver Figma hi-fi mockups for all 50 screens across 4 platforms (Desktop / Tablet / Android / iOS) based on the client's new design brief. STRETCH: Begin implementation of the design system in code if design bandwidth permits — otherwise implementation moves to Sprint 2.
Day | Date | Day of Week | Task / Activity | Description | Owner | Contact (if issue) | Status | Notes (client can add)
Day 1 | 01 Jul 2026 | Wednesday | Sprint 1 Planning + Design Brief Review | Sprint 1 planning call at 10 AM. Walk through the client's new design brief for all 50 screens. Confirm platform breakdown (Desktop / Tablet / Android / iOS). Set up shared Figma workspace. Hand over the shared Excel tracker to Arial. | Hitansu | Hitansu — +91 98270 98057 | Done
Day 2 | 02 Jul 2026 | Thursday | Design Tokens + Style Guide (Figma) | Extract colours, typography, spacing scale, iconography, elevation and grid system from the client's design brief. Build a design-tokens Figma page (Foundations). Confirm dark/light mode strategy. | Hitansu | Hitansu — +91 98270 98057 | Done
Day 3 | 03 Jul 2026 | Friday | Client Sync Meeting + Component Library (Figma) | Today 3 PM: ad-hoc client sync — confirm design direction and any brand-asset updates. Then: build the shared Figma UI component library (buttons, inputs, cards, chips, nav bars, tabs, modals, toasts) so all 50 screens compose from the same primitives. | Mahender | Mahender — +91 79894 78549 | In Progress
Day 4 | 04 Jul 2026 | Saturday | — Weekend — | Off (Saturday) | — | — | Pending
Day 5 | 05 Jul 2026 | Sunday | — Weekend — | Off (Sunday) | — | — | Pending
Day 6 | 06 Jul 2026 | Monday | Monday Sync + Desktop Screens 01–08 (Customer Portal) | 10 AM: Weekly Monday Sync with Arial (30 min Zoom). Then: hi-fi Desktop mockups — Customer Portal set (Home dashboard, Book Service wizard, Ticket detail, AMC viewer, Payment checkout, Profile, Notifications, Help & Support). | Both | Mahender — +91 79894 78549 / Hitansu — +91 98270 98057 | Upcoming
Day 7 | 07 Jul 2026 | Tuesday | Desktop Screens 09–16 (Ops Manager + CRM Agent) | Hi-fi Desktop mockups — Ops Manager triage board, engineer assign, tickets list, quote approval; CRM Agent workbench (offers, tickets, parts approval, customer 360, activity log). | Hitansu | Hitansu — +91 98270 98057 | Upcoming
Day 8 | 08 Jul 2026 | Wednesday | Desktop Screens 17–20 (Admin + Analytics) + Interactive Prototype | Hi-fi Desktop mockups — Admin Earnings dashboard, Revenue Trends, SLA Performance, Team Analytics + Exportable Reports. Wire up an interactive Figma prototype linking Desktop screens end-to-end. | Hitansu | Hitansu — +91 98270 98057 | Upcoming
Day 9 | 09 Jul 2026 | Thursday | Tablet Screens 21–30 (all roles) | Reflow the Desktop screens for Tablet canvas (768–1023px). Customer / Ops / CRM tablet variants — 10 screens total. Confirm responsive breakpoints with Arial. | Hitansu | Hitansu — +91 98270 98057 | Upcoming
Day 10 | 10 Jul 2026 | Friday | Android Screens 31–40 + Mid-week Design Review | Hi-fi Android mockups — Customer app (Home, Booking, Ticket detail, AMC, Payment) + Engineer app (My Jobs, Job detail, Live navigation, Parts checklist, Job-complete flow). Internal design review with Mahender before weekend. | Hitansu | Hitansu — +91 98270 98057 | Upcoming
Day 11 | 11 Jul 2026 | Saturday | — Weekend — | Off (Saturday) | — | — | Pending
Day 12 | 12 Jul 2026 | Sunday | — Weekend — | Off (Sunday) | — | — | Pending
Day 13 | 13 Jul 2026 | Monday | Monday Sync + iOS Screens 41–50 + STRETCH: Begin design-system code | 10 AM: Weekly Monday Sync with Arial. Hi-fi iOS mockups — Customer app (5 screens) + Engineer app (5 screens) mirroring Android with iOS-native patterns (SF Symbols, navigation, etc.). STRETCH: if design bandwidth permits, begin implementing the design system in code (Tailwind theme + reusable React components for Desktop). Otherwise moves to Sprint 2. | Both | Mahender — +91 79894 78549 / Hitansu — +91 98270 98057 | Upcoming
Day 14 | 14 Jul 2026 | Tuesday | Sprint 1 Demo + Sign-off + Sprint 2 Planning | 30 min Zoom demo with Arial — walk through all 50 Figma screens across 4 platforms + interactive prototype. Sprint 1 sign-off form. If design-system code was started (STRETCH), demo the working component library. Decide Sprint 2 scope (full implementation of approved designs). | Both | Mahender — +91 79894 78549 / Hitansu — +91 98270 98057 | Upcoming
Status Legend: | Done | In Progress | Upcoming / Pending | Blocked
📐 Sprint 1 Screen Breakdown — 50 screens total across 4 platforms
Desktop (Web Portal) |  |  | 20 screens | Customer Portal 8 + Ops/CRM 8 + Admin/Analytics 4
Tablet |  |  | 10 screens | Reflowed responsive layouts for Customer, Ops and CRM roles
Android |  |  | 10 screens | Customer app 5 + Engineer app 5
iOS |  |  | 10 screens | Customer app 5 + Engineer app 5 (native SF/SwiftUI patterns)

## Team & Contacts
TEAM & CONTACTS — Who to reach for what
Name | Role | Owns / Responsible For | Phone / WhatsApp | Email | Available Hours (IST)
Mahender Vengala | Project Lead & Delivery Manager | Overall project delivery, client communication, design reviews, Razorpay integration, WhatsApp backend, deployment | +91 79894 78549 | vengalamahender83@gmail.com | Mon–Sat 09:30 – 19:30 (urgent 24×7 on WhatsApp)
Hitansu Parichha | Technical Lead (Full-stack + DevOps + UI/UX) | Figma design system, Frontend (Web / Android / iOS), backend APIs, DevOps, App Store / Play Store submissions | +91 98270 98057 | hparichha@arialsolution.com | Mon–Sat 09:30 – 19:30 (urgent 24×7 on WhatsApp)
When to contact whom
Figma design questions, screen feedback, component library changes |  |  |  | Hitansu — +91 98270 98057 (first responder)
Any issue with the deployed app (down / slow / bug in production) |  |  |  | Mahender — +91 79894 78549 (first responder)
Frontend / mobile UI bug, iOS or Android crash, App Store issue |  |  |  | Hitansu — +91 98270 98057
Razorpay payment failure, WhatsApp not sending, SMS OTP not arriving |  |  |  | Mahender — +91 79894 78549
AMC contract screen bug, engineer tracking map issue |  |  |  | Hitansu — +91 98270 98057
Invoicing / payment milestone / commercial questions |  |  |  | Mahender — +91 79894 78549
Server access / infra questions (Arial's server) |  |  |  | Both — WhatsApp group
Feature request / new requirement (goes into next sprint backlog) |  |  |  | Both — write in shared Excel tracker (Sheet 1 Notes column)

## Meetings
MEETINGS & CALLS — Weekly Monday cadence
Date | Day | Time (IST) | Meeting Type | Attendees | Agenda | Status | Meeting Summary (Arial to fill in)
01 Jul 2026 | Wednesday | 10:00 AM | Sprint 1 Kick-off + Design Brief Walk-through | Mahender, Hitansu, Pradeep (Arial) | Sprint 1 planning, review of client's new design brief for 50 screens x 4 platforms, tracker handover. | Done | Sprint 1 committed as a DESIGN SPRINT. Scope: 50 hi-fi Figma screens across Desktop / Tablet / Android / iOS. Stretch: begin design-system code. Tracker handed over.
03 Jul 2026 | Friday | 03:00 PM | Client Sync (Ad-hoc) — Design Direction Check | Mahender, Hitansu, Pradeep (Arial) | Confirm design direction from the client's brief. Any brand-asset updates. Approve component library approach. | Done
06 Jul 2026 | Monday | 10:00 AM | Weekly Monday Sync — Desktop Progress Review | Mahender, Hitansu, Pradeep (Arial) | Progress on design tokens + component library. Kickoff of Desktop hi-fi mockups (screens 01–08 Customer Portal). | Upcoming
13 Jul 2026 | Monday | 10:00 AM | Weekly Monday Sync — All-Platform Design Review | Mahender, Hitansu, Pradeep (Arial) | Review Desktop (20) + Tablet (10) + Android (10) screens. Prepare for iOS + Sprint demo. Discuss STRETCH: whether to begin implementation now or defer to Sprint 2. | Upcoming
14 Jul 2026 | Tuesday | 04:00 PM | Sprint 1 Demo + Sign-off + Sprint 2 Planning | Mahender, Hitansu, Pradeep, Kesav (Arial) | Walk through all 50 Figma screens + interactive prototype. Demo design-system code (if STRETCH completed). Sprint 1 sign-off form. Plan Sprint 2 (full implementation of approved designs). Invoice for M2 milestone. | Upcoming
20 Jul 2026 | Monday | 10:00 AM | Weekly Monday Sync + Sprint 2 Kickoff | Mahender, Hitansu, Pradeep (Arial) | Sprint 2 planning — full implementation of approved designs starting with Desktop, then Android, then iOS, then Tablet. | Upcoming
22 Jul 2026 | Wednesday | 03:00 PM | Further Features Discussion (Phase 2) | Mahender, Hitansu, Pradeep, Kesav (Arial) | Discuss Phase 2 scope: inventory module, accounting integration, multi-language, IoT telemetry. | Upcoming
27 Jul 2026 | Monday | 10:00 AM | Weekly Monday Sync — Sprint 2 Mid-point | Mahender, Hitansu, Pradeep (Arial) | Implementation progress on Desktop + Android. Blocker discussion. | Upcoming
28 Jul 2026 | Tuesday | 04:00 PM | Sprint 2 Demo + Sign-off | Mahender, Hitansu, Pradeep, Kesav (Arial) | Demo of implemented Desktop + Android. Sign-off form. Invoice for M3 milestone. | Upcoming
03 Aug 2026 | Monday | 10:00 AM | Weekly Monday Sync + Sprint 3 Kickoff | Mahender, Hitansu, Pradeep (Arial) | Sprint 3 planning — iOS + Tablet implementation + core backend wiring. | Upcoming
⭐ NEXT MONDAY SYNC: 06 Jul 2026 @ 10 AM IST — Desktop screens kickoff (Mahender, Hitansu, Pradeep)
📝 Note for Arial team: After every meeting, please paste a short summary of what was discussed and any action items into the 'Meeting Summary' column (yellow cells).

## Payments
PAYMENT SCHEDULE — Professional Package ₹6,79,500
Milestone | Amount (INR) | % | Trigger / Condition | Expected Date | Invoice Sent? | Status
M1 — Kick-off | ₹1,35,900 | 20% | On signing of SOW v3 | 30 Jun 2026 | Yes | Paid
M2 — Sprint 1 (Design) Sign-off | ₹1,35,900 | 20% | All 50 Figma screens across 4 platforms approved by Arial | 14 Jul 2026 | Pending | Upcoming
M3 — Sprint 2 (Implementation Start) Sign-off | ₹1,35,900 | 20% | Desktop + Android implementation demoed and signed off | 28 Jul 2026 | Pending | Upcoming
M4 — Dev Complete / Demo | ₹1,35,900 | 20% | All platforms implemented on Staging, core modules live, demo sign-off | 22 Sep 2026 (end of Sprint 6) | Pending | Upcoming
M5 — UAT & Go-Live | ₹1,35,900 | 20% | UAT sign-off, Play Store live, App Store live, Web live | 06 Oct 2026 (end of Sprint 7) | Pending | Upcoming
TOTAL | ₹6,79,500 | 100% | Full contract value — paid across 5 equal milestones of ₹1,35,900
💰 NEXT PAYMENT REQUEST: M2 — Sprint 1 (Design) Sign-off — ₹1,35,900 — Expected by 14 Jul 2026 (all 50 Figma screens approved). Please arrange NEFT / IMPS transfer within 5 business days of sign-off.

## Progress Dashboard
SPRINT 1 (DESIGN SPRINT) — PROGRESS DASHBOARD
Status | Task Count
Done | 2
In Progress | 1
Pending / Upcoming | 11
Blocked | 0
TOTAL
Platform | Screens
Desktop (Web) | 20
Tablet | 10
Android | 10
iOS | 10
✅ Sprint 1 Completion: 2 / 14 tasks done = 14.3%
🚀 STRETCH GOAL: If design bandwidth permits, begin implementing the design system in code (Tailwind theme + reusable React components) in the last 2 days of Sprint 1. Otherwise, implementation begins in Sprint 2.